## START HERE
ALPHA DENTAL SYSTEM
Launch Readiness Matrix
Prepared 10 August 2026 · Companion to Alpha-Dental-WebApp-Feature-Inventory.pdf
THE IDEA | You have 160 features. You cannot make 160 features perfect before you launch, and you do not need to. Nobody is ever embarrassed by a feature the customer did not click. You get embarrassed when the thing they DID click threw an error.
So every feature is sorted into three buckets. Make the first bucket flawless. Make sure the second does not crash. Hide the third.
P0 — MUST BE FLAWLESS | The daily loop a clinic runs on, plus your demo path. If one of these breaks, the clinic stops working or the sale dies. Test every one, by hand, before a paying customer logs in.
P1 — MUST NOT BREAK | Present and occasionally used, but not what you are selling. Open each one once. Fix only crashes and wrong numbers. Ignore cosmetic issues.
P2 — HIDE OR IGNORE | Not needed by a single-chair Egyptian clinic at launch, or not safe to expose yet. Turn it off in the plan, or simply never demo it.
HOW TO USE THIS | Work down the P0 sheet. For each row: do what the 'How to test it' column says, compare against 'What must happen', then set Status. Anything that fails, write what you saw in Notes and set the Severity.
Only YOU edit the coloured columns: Status, Severity, Notes, Fixed on. Everything else is reference.
BEFORE YOU START | Read the BLOCKERS sheet first. Three of those are decisions, not bugs — you should settle them before you spend a day testing.
RULE FOR TESTING | Test with REAL data from a real clinic day, not with 'test test test'. Most of these failures only appear with real Arabic names, real Egyptian phone numbers, and real money.
LIVE PROGRESS
P0 features to test
P0 passed
P0 failed
P0 not tested yet
P0 ready %
Blockers still open
You are ready to take a paying customer when P0 ready % is 100% and Blockers still open is 0.

## BLOCKERS
BLOCKERS AND DECISIONS — settle these before you test anything else
Found by reading your code on 10 Aug 2026. Items marked DECISION are business calls only you can make.
# | What | The problem | What I recommend | Type | Severity | Status | Your decision / notes
1 | Public patient portal leaks records | On your public booking page, anyone who types a phone number sees that person's appointments AND their outstanding balance. No code, no verification, no login. A spouse, an employer, or someone typing random numbers can read a patient's dental debt. | Turn the 'My Records' half of the public page OFF before launch. Re-enable later only behind a WhatsApp one-time code. Under Law 151/2020 health data is sensitive — this is the item I would least like a competitor to find. | BUG | Critical | Open
2 | Public booking can be abused | The booking endpoint has no rate limit, so anyone can fill a clinic's whole calendar with fake bookings. It also blocks a time slot for ALL dentists once one books it, and a CANCELLED appointment keeps its slot blocked forever. Every booking silently creates a patient record. | Either keep online booking off for launch, or add a rate limit, check the slot per dentist, and ignore cancelled appointments. Off is the safe answer for week one. | BUG | High | Open
3 | Email reports do not exist | Settings > Alerts offers 'Email Reports — daily and weekly summaries' with an email field. There is no email code in the project at all. A customer will fill it in and wait forever for reports that will never arrive. | Hide the email section from the Alerts screen. A setting that lies is worse than a missing feature — the customer blames you twice: once for not sending, once for pretending. | BUG | High | Open
4 | Clock-in fails intermittently | Your own testers report this. Attendance feeds payroll, so every failure becomes an argument between a staff member and the clinic owner, with your software in the middle. | Hide the whole Attendance module for launch. It is not part of your pitch and it is the fastest way to lose a customer's trust. Fix it properly in month two, then sell it as a new feature. | DECISION | High | Open
5 | Vercel plan | You are on the free Hobby plan. Hobby forbids commercial use, and caps how long a request may run at roughly 10 seconds. None of your AI routes raise that limit. Revenue Recovery on a clinic with real history will time out with no useful error. | Upgrade to Pro BEFORE the first paying customer, and set maxDuration on the five /api/ai routes. About 20 USD a month. Half an hour of work. | FIX | High | Open
6 | Multi-tenant isolation is unproven | Your three clinics run the OLD system, which used a separate Firebase per clinic. v3 puts every clinic in one database. The rules look correct to me, but no real clinic has ever tested them. | Test 1.1 on the P0 sheet is the single most important test in this workbook. Two clinics, two logins, confirm neither can see the other anywhere — list, search, reports, AI. Do it before anything else. | TEST | Critical | Open
7 | WhatsApp gateway ban risk | You send through Wapilot, an unofficial gateway. Meta can restrict a number that automates WhatsApp. If it is the clinic's own number, the clinic loses contact with its patients. | Put it in writing in your terms: use a dedicated clinic number, never the owner's personal one, and the number may be restricted by WhatsApp. Also ship the click-to-send option so clinics with no papers have a zero-risk path. | DECISION | High | Open
8 | Reports read the whole database | The reports screen loads every ledger row, every patient and all staff on each open and each date change. Fine today, slow and costly at two years of data. | Half a day: query by date range instead. Do it before you have a clinic with history, not after. | FIX | Medium | Open
9 | No error monitoring | When something breaks for a clinic at 9pm, you find out only if they call you. Some will not call — they will just stop using it. | Add Sentry (free tier) before launch. One afternoon. You want to know about breakage before the dentist does. | FIX | Medium | Open
10 | Backup and restore never tested | Losing a clinic's patient records is the only failure you cannot recover from, commercially or morally. | Export one clinic and restore it into an empty clinic, once, by hand, before launch. Then write down the steps. | TEST | Critical | Open
11 | Interface changes constantly | Your testers' single biggest complaint over six months. Clinic staff are not early adopters; a moved button costs a real minute with a real patient waiting. | Freeze the interface now. Batch changes into releases every second Tuesday, with a two-line note in Arabic saying what changed. | DECISION | Medium | Open
12 | No company, no invoice | You are collecting personally. Clinics that are registered businesses will ask for a proper invoice, and Fawry/Paymob both require a registered entity. | Fine for the first customers by InstaPay. Register within 90 days. Not a launch blocker, but put a date on it now. | DECISION | Medium | Open

## P0 Must be flawless
P0 — MUST BE FLAWLESS. Every row here must pass before a paying customer logs in.
ID | Module | Feature | How to test it | What must happen | Severity if failed | Status | What you saw | Fixed on
0.0 | EXAMPLE | This row shows the format — delete it or leave it | Do the thing described here, step by step | Compare against this | High | Fail | Balance showed 600 but finance showed 1000 | 12 Aug
1.1 | Platform | Clinic data isolation ** THE MOST IMPORTANT TEST ** | Create two test clinics, A and B, with different logins. In clinic A create a patient called TEST-ALPHA and add a payment. Sign in as clinic B. | Clinic B finds NOTHING belonging to A — not in the patient list, not in search, not in finance, not in reports, and not by asking the AI assistant. Repeat the AI part specifically. |  | Not tested
1.2 | Platform | Sign in and sign out | Sign in with the right password, then a wrong one. Sign out, then press the browser Back button. | Right password works. Wrong password gives a clear message in both languages. Back after sign-out shows the login page, never clinic data. |  | Not tested
1.3 | Platform | New clinic onboarding | Register a brand-new account from scratch and create a clinic, exactly as a customer would. | Lands on the dashboard as Admin. Clinic appears in your Super Admin list with the right tier. |  | Not tested
1.5 | Platform | Roles | Create one user of each role: Dentist, Assistant, Receptionist. Sign in as each in turn. | Each sees only the menu their role allows. No blank pages, no error screens. |  | Not tested
1.6 | Platform | Permissions actually block | Create a Receptionist with no finance permission. Sign in as her and type /finance and /reports straight into the address bar. | Both refused. Hiding a menu item is not security — the owner is buying the guarantee that his receptionist cannot see his revenue. |  | Not tested
1.7 | Platform | Tier limits | Set a test clinic to Basic (3 staff). Try to add a fourth staff member. | Blocked with a clear upgrade message. Not a crash, not a silent failure. |  | Not tested
1.9 | Platform | Super Admin controls | As super admin: change a clinic's tier, open the clinic, then return to the super admin area. | Tier change takes effect immediately inside the clinic. Entering and leaving leaves no trace of the other clinic. |  | Not tested
2.1 | Language | Arabic and right-to-left | Switch to Arabic and walk every P0 screen: dashboard, patients, appointments, finance, reports, settings. Then export a PDF from each. | Layout flips cleanly, no overlapping text, no English left in buttons, tables not reversed. Arabic in PDFs renders as letters, not boxes. |  | Not tested
2.5 | Language | Confirms and toasts | Delete something and press Cancel. Delete again and confirm. | Cancel changes nothing. Confirm deletes and shows a success message. |  | Not tested
3.1 | Dashboard | Desktop dashboard numbers | Set up a day with 3 appointments and 2 payments. Open the dashboard and add the payments up by hand. | Daily income matches your hand total to the pound. Appointment count and status counts are correct. |  | Not tested
3.2 | Dashboard | Mobile dashboard | Open it on a real phone, in Arabic, on mobile data — not a narrow desktop window. | Readable, tappable, numbers identical to desktop. This is the screen the clinic owner will actually look at. |  | Not tested
3.3 | Dashboard | Actions from the schedule row | From a dashboard appointment row: change stage, take a payment, print a receipt. | All three work without leaving the page, and each change shows up in the ledger. |  | Not tested
3.5 | Dashboard | Quick actions | Use New Patient and Quick Pay from the header. | Patient is created and immediately searchable. Payment appears in the patient's ledger and in today's income. |  | Not tested
4.1 | Patients | Patient search | Search one patient five ways: full name, first name only, last name only, middle of the name, part of the phone. Do it with an Arabic name. | All five find the patient. Test a name with more than one common Arabic spelling — this is where search usually disappoints a receptionist. |  | Not tested
4.2 | Patients | Register a patient | Register a patient with a normal Egyptian mobile number. | Saved, searchable, phone stored in full international form. |  | Not tested
4.3 | Patients | All patient tabs load | Open a patient who has data in every tab: overview, clinical, timeline, finance, x-rays, prescriptions. | Every tab loads with no blank screen and no error. |  | Not tested
4.5 | Patients | Phone number formats | Enter the same number as 01012345678 and as +201012345678 on two patients. | Both end up in the same format, and WhatsApp reaches both. |  | Not tested
4.11 | Patients | Patient sources | Register three patients with three different sources, then run the Patient Sources report. | Each appears under the correct source with the correct money. This is a feature you are selling — it has to be exact. |  | Not tested
5.1 | Appointments | Calendar matches your schedule | Set hours 10:00-22:00, 30-minute slots, Friday off. Open the calendar. | Grid matches exactly. Friday shows as closed. No slots outside opening hours. |  | Not tested
5.2 | Appointments | Drag and drop | Drag an appointment to a different day and time, then refresh the page. | It stays where you dropped it, and the patient's record shows the new time. |  | Not tested
5.3 | Appointments | Booking | Book for an existing patient, then for a brand-new patient created during booking. | Both save and appear on the calendar and on the patient record. |  | Not tested
5.4 | Appointments | Double booking | Try to book two appointments in the same slot with the same dentist. | Either blocked or clearly warned. Decide which you want and make it behave the same way every time. |  | Not tested
5.6 | Appointments | Workflow stages | Take one appointment through every stage: Scheduled, Confirmed, Checked In, In Chair, Completed. | Each stage saves, keeps its colour, and shows the right Arabic label. |  | Not tested
5.7 | Appointments | Check-in | Mark a patient as Checked In. | Arrival time is recorded and the patient shows as waiting. |  | Not tested
5.13 | Appointments | Appointment side panel | Click an appointment on the calendar. | Panel opens with the right patient, the right ledger, and a working payment button. |  | Not tested
6.1 | Clinical | Clinical notes persist | Add a note with a service to a visit. Close everything and reopen the patient the next day. | Note is there, dated the treatment date, credited to the right dentist. |  | Not tested
6.2 | Clinical | Service editor feeds the ledger | Add a service with a price to a visit. | The price appears in the patient ledger and in the day's finance totals. |  | Not tested
6.8 | Clinical | Write a prescription | Write a prescription with three drugs, one of them typed in by hand rather than picked from the list. | All three save, with dose and instructions, signed by the chosen dentist. |  | Not tested
6.9 | Clinical | Prescription print, PDF and WhatsApp | Print it, download the PDF, and send the PDF to your own number by WhatsApp. | Arabic renders correctly in the PDF (this is the most common failure). Letterhead correct. The file actually arrives. |  | Not tested
6.11 | Clinical | Prescription letterhead | Set the Rx header in Settings, in Arabic, then print. | Header appears exactly as typed, correctly shaped, on the printed page. |  | Not tested
7.1 | Finance | Ledger arithmetic | Charge a procedure of 1000. Take a payment of 400. | Patient balance shows 600 owed. Today's cash shows 400, NOT 1000. Confirm both screens agree. |  | Not tested
7.2 | Finance | Finance KPIs match reality | Take one full real day of entries and add them up by hand on paper. Compare with the KPI cards. | They match to the pound. Do this once properly before you sell anything — this is the number the owner checks. |  | Not tested
7.3 | Finance | Daily, monthly, range | Switch between the three views on the same data. | Totals change correctly and never include entries outside the period. |  | Not tested
7.4 | Finance | Add, edit, delete | Add an expense, edit it, then delete it. | Each works, and the deleted entry disappears from KPIs AND from reports. |  | Not tested
7.6 | Finance | Discount | Charge 1000 with a 200 discount. | Ledger shows what was actually charged, the discount stays visible, and reports agree with the ledger. |  | Not tested
7.8 | Finance | Quick payment | Take a payment from the dashboard rather than the finance screen. | It appears in the patient ledger, today's income, and that day's report. |  | Not tested
7.9 | Finance | Patient balance | Open a patient with several procedures and several payments. Add it up by hand. | Balance equals total charged minus total paid. No rounding drift. |  | Not tested
7.10 | Finance | Receipt | Print a receipt and send a receipt summary by WhatsApp. | Amounts, Arabic and clinic details all correct on both. |  | Not tested
8.1 | Reports | Date range behaves | Run every report for last month, then for a custom range. | Numbers change with the range and never include anything outside it. |  | Not tested
8.2 | Reports | Service analysis | Pick one week and check the report against the ledger by hand. | Matches exactly. Nothing counted twice, nothing missing. |  | Not tested
8.3 | Reports | Dentist performance | Two dentists, several procedures each, including one transferred between visits. | Every procedure credited to the correct dentist, none double-counted. |  | Not tested
8.5 | Reports | Reports agree with Finance | Run Clinic Overview for a month, then open Finance for the same month. | The two screens show the same revenue. If they disagree, a customer WILL find it, and you lose the money conversation. |  | Not tested
8.6 | Reports | Report PDF export | Export each of the four reports, in Arabic and in English. | Arabic renders as readable letters. Clinic name correct. Nothing cut off at the page edge. |  | Not tested
11.1 | WhatsApp | Message actually sends | Send a booking confirmation to your own number. | Arrives within a minute, correct Arabic, correct details. |  | Not tested
11.2 | WhatsApp | Template editing | Edit a template in Settings, save, and send again. | Your edit appears in the delivered message. |  | Not tested
11.3 | WhatsApp | Merge fields | Send all four types: new booking, reschedule, cancel, payment received. | Patient name, dentist, date, time and amount all correct. No {{placeholder}} text left visible to the patient. |  | Not tested
11.4 | WhatsApp | 24-hour reminder job | Book two appointments for tomorrow, then trigger the reminder job. | Exactly one reminder per patient. Not zero, not two. Run it twice and confirm nobody gets a duplicate. |  | Not tested
11.9 | WhatsApp | Opt-out is honoured everywhere | Set a patient to opted out. Then try every path: manual send, booking confirmation, payment message, and the automated reminder job. | No message reaches them from ANY path. One leak here is a complaint you cannot answer. |  | Not tested
13.3 | AI | Confirmation gate | Ask the assistant to delete a record, then reject the confirmation. | It asks first, and rejecting changes nothing at all. |  | Not tested
13.5 | AI | Credit metering | Use the assistant until credits run low, then past the limit. | Counter decreases correctly, stops cleanly at the limit with a clear message, and does not keep spending your money. |  | Not tested
13.7 | AI | Revenue Recovery is accurate | Deliberately record a treatment in clinical notes with no ledger entry. Run the scan. Then check EVERY finding it reports by hand. | It finds the one you planted, and every other finding is genuinely true. One false accusation that a dentist forgot to invoice will destroy his trust in the whole product. |  | Not tested
13.8 | AI | Reactivation list and drafts | Set the dormancy threshold. Run the scan and read every draft message. | The patient list is correct, the Arabic is natural, names are right, and nothing sends until you approve it. |  | Not tested
14.1 | Settings | Clinic profile flows everywhere | Fill in every clinic field, then check a receipt, a prescription and a report. | Name, phone, address and currency correct on all three. |  | Not tested
14.2 | Settings | Price list | Enter your real price list, then book and charge from it. | Prices flow correctly into the ledger without retyping. |  | Not tested
14.3 | Settings | Schedule drives everything | Change opening hours and off days. | Calendar and online booking both respect the change immediately. |  | Not tested
14.4 | Settings | User management | Create a staff member, change their permissions, then remove them. | Login works, permissions apply immediately, and removal blocks access. |  | Not tested
15.3 | Security | Direct URL access | As a Receptionist, type these into the address bar: /finance, /reports, /settings, /ai/revenue, /superadmin. | Every one refused. This is the test that protects your reputation if a clinic ever has a dispute with staff. |  | Not tested
15.5 | Security | Automation endpoint is protected | Open the reminder job URL in a normal browser with no secret. | Refused. Anyone who finds the URL must not be able to make your system send messages. |  | Not tested
16.1 | Operations | Backup and restore | Export one clinic's data and restore it into an empty clinic. | It works, and you have now done it once. This is the only failure you can never apologise your way out of. |  | Not tested
16.2 | Operations | Error monitoring | Break something on purpose in a test clinic. | You learn about it from your monitoring, not from a phone call from a dentist. |  | Not tested

## P1 Must not break
P1 — MUST NOT BREAK. Open each once. Fix crashes and wrong numbers only. Ignore anything cosmetic.
ID | Module | Feature | Quick check | Status | Notes
1.4 | Platform | Join requests | Request to join a clinic, approve it as Admin. | Not tested
1.10 | Platform | Clinic switcher | Switch between two clinics on one login. | Not tested
1.11 | Platform | Activity log | Change a setting, confirm it is logged. Confirm an Admin cannot delete the entry. (Worth demoing — it is a selling point.) | Not tested
2.3 | Language | Interface preferences | Switch editor between modal and drawer. | Not tested
3.4 | Dashboard | Weekly schedule view | Open it, check it matches the calendar. | Not tested
3.6 | Dashboard | Daily briefing card | Open on a day with appointments and an old balance. | Not tested
3.8 | Dashboard | Notification bell | Trigger an alert, confirm it appears. | Not tested
4.6 | Patients | WhatsApp opt-out toggle | Toggle it, confirm it saves (behaviour tested in 11.9). | Not tested
4.7 | Patients | CRM timeline | Check messages and events appear in the right order. | Not tested
4.8 | Patients | Media gallery | Upload an x-ray, view it, delete it. | Not tested
4.10 | Patients | Google review request | Send one to your own number. | Not tested
4.12 | Patients | Delete patient | Delete a test patient, confirm it is logged. | Not tested
5.5 | Appointments | Treatment duration | Set a 60-minute treatment, confirm the calendar blocks 60 minutes. | Not tested
5.8 | Appointments | Late patient prompt | Let an appointment go past its time. | Not tested
5.10 | Appointments | Patient history drawer | Open from the calendar. | Not tested
5.12 | Appointments | Filters | Filter by dentist and by status. | Not tested
5.18 | Appointments | Visit reasons | Add one, confirm it appears when booking. | Not tested
6.3 | Clinical | Transfer / continue treatment | Move a service to another visit, check the ledger still balances. | Not tested
6.4 | Clinical | Odontogram | Chart a few teeth and surfaces, reopen. Demo asset — must look good, not be perfect. | Not tested
6.5 | Clinical | Diagnosis catalogue | Search and apply a diagnosis. | Not tested
6.7 | Clinical | Diagnosis report PDF | Export one, check the chart image renders. | Not tested
6.10 | Clinical | Prescription history | Reprint an old prescription. | Not tested
6.13 | Clinical | Lab management | Add a lab with prices, attach to a procedure. | Not tested
7.5 | Finance | Filters and paging | Filter by dentist and patient on a long ledger. | Not tested
7.7 | Finance | Lab fee and commission | Check one procedure's profit calculation by hand. | Not tested
7.11 | Finance | Ledger PDF export | Export a filtered view. | Not tested
8.7 | Reports | Excel export | Export and open in Excel, check Arabic. | Not tested
11.5 | WhatsApp | Documents by WhatsApp | Send a lab order and a receipt. | Not tested
11.8 | WhatsApp | Message log | Confirm every send appears on the patient timeline. | Not tested
12.2 | Alerts | In-app alerts | Trigger patient-arrival and low-stock alerts. | Not tested
13.1 | AI | Chat assistant | Ask three real questions. Your testers found this the least useful feature — do not lead with it. | Not tested
13.6 | AI | Daily briefing | Open it on a real day. | Not tested
13.9 | AI | Recalls and stock | Confirm it says clearly when the setting is not configured. | Not tested
13.10 | AI | Unresolved appointments | Leave an old appointment unmarked, confirm it is listed. | Not tested
14.5 | Settings | Recall interval | Set it, confirm the recall list uses it. | Not tested
14.6 | Settings | Patient sources list | Add and remove a source. | Not tested
15.4 | Security | Read-only mode | Put a test clinic into read-only, confirm writes are blocked. | Not tested
15.6 | Security | File storage | Confirm an uploaded x-ray is not readable from another clinic. | Not tested

## P2 Hide or ignore
P2 — HIDE OR IGNORE. Do this BEFORE the first customer logs in, not after.
ID | Feature | Action | Why | Done
Whole module | Attendance and payroll (10.1-10.11) | HIDE | Clock-in fails intermittently and it feeds payroll. Highest-risk module you own. Re-launch it in month two as a new feature. | No
Whole module | Inventory (9.1-9.7) | LEAVE ON, DO NOT DEMO | Works, but a single-chair clinic does not track stock formally. Not part of your pitch. | No
Whole module | Orthodontics (6.12) | LEAVE ON, DO NOT DEMO | Genuinely good, but only relevant to ortho cases. Mention it only if the dentist raises ortho. | No
6.6 | Periodontal charting | LEAVE ON, DO NOT DEMO | Requires dentist data entry, which your target dentists will not do. | No
5.16 | Public patient records lookup | TURN OFF NOW | Privacy leak. See BLOCKERS row 1. | No
5.15 | Public online booking page | TURN OFF FOR LAUNCH | No rate limit and slot logic is wrong. See BLOCKERS row 2. Re-enable once fixed — it is a good differentiator. | No
12.3 | Email reports (in Settings > Alerts) | HIDE THE SECTION | No email code exists. See BLOCKERS row 3. | No
12.1 | Push notifications | LEAVE ON, DO NOT DEMO | Browser permissions make this unreliable across devices. Do not promise it in a sale. | No
12.4 | Reception summon | LEAVE ON, DO NOT DEMO | Nice touch, needs two devices to show. Not worth demo time. | No
13.11 | No-show risk | HIDE UNTIL DATA EXISTS | Needs months of attendance history. On a new clinic it says nothing useful, which makes the AI look empty. | No
13.12 | AI treatment plan generation | LEAVE ON, DO NOT DEMO | Clinical AI suggestions to a dentist is a credibility risk you do not need in week one. | No
13.13 | Voice replies (TTS) | OFF BY DEFAULT | Costs money per character and adds nothing to a sale. Leave it available, default off. | No
13.14 | Reception avatar assistant | HIDE FOR LAUNCH | Your testers already told you the chat bubble was not useful. Do not open with an animated version of it. | No
13.4 | AI long-term memory | LEAVE ON, DO NOT DEMO | Hard to show in a demo, easy to demo badly. | No
1.12 | Database repair tool | HIDE FROM CUSTOMERS | Internal tool. A button called 'repair database' frightens a buyer. | No
1.13 | Data migration screen | HIDE | No migration at launch. A half-working migration button is a data-loss risk. | No
4.9 | Patient time tracker | LEAVE ON, DO NOT DEMO | Minor feature, adds demo time without adding value. | No
5.9 | Waiting mood tracker | LEAVE ON — MENTION ONLY | Charming and memorable, but it is a story, not a reason to buy. One line in the demo, no more. | No
5.11 | Visit rating | LEAVE ON, DO NOT DEMO | Minor. | No
2.2 | Theme settings | LEAVE ON, DO NOT DEMO | Cosmetic. | No

## Demo script
THE 12-MINUTE DEMO — make these screens flawless and the rest barely matters
Same demo every time. A demo you have given fifty times does not surprise you in front of a customer.
Time | Screen | What you do | What you say
0:00 | Open on the phone, in Arabic | Do not start on a laptop. Start on YOUR phone, showing YOUR clinic's real day. | "This is my clinic, right now. I built this because I had the same problem you have."
0:30 | Dashboard — today's money | Today's income, patient count, appointment status. | "Every morning I know exactly where I stand before I open the door."
2:00 | Reports — Patient Sources | Show which sources brought patients and what each one was worth. | "This is the one that changed things for me. I was paying for advertising that brought me nothing, and I could not see it."
4:00 | Reports — Dentist and Service | Which treatments make money, which dentist produces what. | "You cannot fix what you cannot see."
5:30 | Revenue Recovery | Run the scan live on seeded demo data. Show treatment done but never invoiced. | "This is money you already earned. It is sitting in your notes and never reached your books." — Your single strongest moment. Do not rush it.
7:30 | Reactivation | Show the lapsed patient list and a draft WhatsApp message awaiting approval. | "In a market this crowded, the cheapest patient is the one who already trusts you."
9:00 | Appointments and check-in | Book, drag to reschedule, check a patient in. | Fast. They already believe this part works.
10:00 | Permissions and the activity log | Show that a receptionist cannot see revenue, and that nobody — not even an Admin — can erase the log. | "Your receptionist cannot see your money, and cannot delete the record of what she did." — Nobody else in this market says this.
11:00 | Price and close | One page, Arabic, on WhatsApp. Founding member price, first 20 clinics, closing date. | "Normal price is 4,800. For the first twenty clinics it is 3,000, and you will never pay full price."
12:00 | Stop talking | Do not demo the odontogram, ortho, inventory or the AI chat unless they ask. | Every extra feature you show is another thing that can go wrong and another reason to hesitate.